## Gnatt
| Term 1 | [6 empty] | Term 2
| Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Documentation
Research Question | Research Question
Gnatt Chart | Gnatt Chart | Ethics Assessment
Prototype Documents
Risk Assessment |  |  | Risk Assessment
Survay Planning |  |  | Survey Development
Risk Assessment
Development
Game Mechanics |  |  |  | Gameplay Mechanics
Wall Generation (PCG tool) | [7 empty] | Term 2 Week 1: Procedural Generation
Static World Created | [6 empty] | Static World
Generated World Setup | [7 empty] | Term 2 Week 5: PCG Level Developemt
Polish | [7 empty] | Term 2 Week 8: Polish
Bug Fixing | [7 empty] | Term 2 Week 7: Bug Fixing
Evaluation and Dissertation
Find participants | [7 empty] | Term 2 Week 6: Find participants
Showcase and intro | [7 empty] | Term 2 Week 6: Showcase and intro
Survey & information gathering | [7 empty] | Term 2 Week 6: Survey & information gathering
Abstract | [7 empty] | Term 2 Week 3: Abstract
Introduction | [7 empty] | Term 2 Week 3: Introduction
Background | [7 empty] | Term 2 Week 3: Background
Methodology | [7 empty] | Term 2 Week 5: Methodology
Result | [7 empty] | Term 2 Week 8: Result
Discussion | [7 empty] | Term 2 Week 9: Discussion
Conclusion | [7 empty] | Term 2 Week 10: Conclusion
Presentation | [7 empty] | Term 2 Week 11: Presentation

## Risk
Risk | Impact | Likelihood | Total Risk Score | Preventative
Theft of equipment |  |  | 3 | Take care with, and when leaving items.
Damaging of equipment |  |  | 3 | Be careful when using or leaving items of equipment.
Illness |  |  | 4 | Wash hands and dress according to winter conditions.
Injury |  |  | 4 | Avoid dangerous and abnormal situations. Ensure to plan ahead.
Lack of testers |  |  | 6 | Reach out to university and other groups to gain access to members to be used in testing.
Burnout |  |  | 5 | Ensure to take time for oneself in order to avoid burnout.
Family Issues |  |  | 5 | Communicate well to avoid issues arising.
Work issues |  |  | 4 | Communicate well to avoid issues arising.
Financial difficulties |  |  | 5 | Plan ahead to avoid surprise expenses that may cause stress and difficulty.
Feature creep |  |  | 6 | Plan ahead and stick to plan unless all planned features and implemented.
| Severe | High
| Medium | Medium
| Mild | Low